## Sheet1
APES PROJECT - TASK LIST - AFTER RESOURCE LEVELLING
[5 empty] | DEPENDENCIES | RESOURCES | PM | BA | Architect | Quality | Developpers | Total Effo | Duration | Duration
[10 empty] | Assurer |  | rt In | (Hours) | (Weeks)
# | TASK | [5 empty] | <---------------------------------HOURS------> |  |  |  |  | Hours
1 | APES PROJECT
2 |  | Management
3 |  |  | Plan Project
4 |  |  |  | Develop Project Plan |  | PM | 52 |  |  |  |  | 50 | 50 | 1
5 |  |  |  | Update Project Plan | 4 | PM | 50 |  |  |  |  | 50
6 |  | M |  | MOV and Objectives Established | 4 | [6 empty] | 46
7 |  |  | Track Project
8 |  |  |  | Prepare Status Reports | 4 | PM | 48 |  |  |  |  | 48
9 |  |  |  | Present Status Reports |  |  | 48 |  |  |  |  | 48
10 |  |  | Perform Daily Project Management Tasks |  |  | PM | 608 |  |  |  |  | 608
11 |  | Design
12 |  |  | Plan Initial Design
13 |  |  |  | Develop Template Design & Details | 4 | A, BA |  | 20 | 20 |  |  | 40 | 17 | 0.5
14 |  |  |  | Plan Out Data Flow Diagram | 13 | A, BA |  | 20 | 20 |  |  | 34 | 17 | 0.5
15 |  |  |  | Plan Out Logical Data Model | 14 | A, BA |  | 10 | 10 |  |  | 20 | 10 | 0.2
16 |  | M |  | Conclude Logical Design | 15
17 |  |  | Plan Out Elaborate Design
18 |  |  |  | Plan Out Physical Model | 16 | A |  |  | 18
19 |  |  |  | Plan Out Data Dictionary | 18 | A |  |  | 18 |  |  | 22 | 22 | 0.3
20 |  | M |  | Conclude Physical Design | 19 | [6 empty] | 22 | 22 | 0.2
21 |  |  | Document Design
22 |  |  |  | Conceive Design | 20 | A
23 |  |  |  | Go Over Design | 22 | QA |  |  | 20 |  |  | 15 | 5 | 0.3
24 |  | M |  | Software Documentation Complete | 23 |  |  |  | 10 | 10 |  | 15 | 7.5 | 0.2
25 |  |  | Design Authorization
26 |  |  |  | Show Design to Client | 24 | PM, A | 12 |  | 20 |  |  | 28 | 16 | 0.4
27 |  | M |  | Have Client Authorize | 26
28 |  | Procurement
29 |  |  | Gather Hardware
30 |  |  |  | Gather Server | 27 | Pur, S
31 |  |  |  | Gather Workstations | 27 | Pur, WS | [6 empty] | 35 | 0.2
32 |  | M |  | Necessary Hardware Acquired | 30, 31 | [7 empty] | 35 | 0.2
33 |  |  | Gather Software |  |  | Pur, DB
34 |  |  |  | Gather Database | 27 | Pur, UIT
35 |  |  |  | Gather User Interface Assembling Equip. | 27
36 |  | M |  | Necessary Software Equip. Acquired | 34, 35 | PM, A, V
37 |  |  |  | Organise and Install HW & SW | 32, 36 |  | 40 |  |  |  |  | 80 | 48 | 1
38 |  | M |  | HW & SW Installation Complete | 37
39 |  |  | Development
40 |  |  |  | Modify Server Performance | 38 | A, DI, D2 |  |  | 172 |  | 310 | 470 | 150 | 6.5
41 |  |  |  | Develop System User Interface | 38 | A, D3, D4 |  |  | 130 |  | 250 | 380 | 110 | 5.1
42 |  |  |  | Show Template to Client | 40, 41 | A, D1, D3 |  |  | 35 |  | 100 | 100 | 30 | 1.5
43 |  | M |  | Necessary Software Installation Accepted | 42
44 |  |  | Acceptance Testing
45 |  |  |  | Produce Acceptane Testing Proposal | 27 | PM, BA, A | 20 | 20 | 20 |  |  | 40 |  | 0.6
46 |  |  |  | Run Acceptance Testing Sessions | 27, 43 | BA, A, D1. D3, C |  | 44 | 24 |  |  | 150 |  | 1.8
47 |  |  |  | Fill Out Test Report | 46 | BA, A, D1, D3 |  | 24 | 24 |  |  | 75 |  | 1
48 |  | M |  | Test Report Completed | 47
49 |  |  |  | Go Over Test Report and Authorize | 48 | BA, A, C |  | 24 | 20 |  |  | 44 | 24 | 1.6
50 |  | M |  | Finalised Software Blueprint Authorized | 49 | [6 empty] | 30
51 |  | Installation
52 |  |  | Develop Installation Plan |  | 27 | PM, A | 24 |  | 26 |  |  | 48 | 26 | 0.7
53 |  |  | Install at Locations |  | 49 | A, D1, D3 |  |  | 48 |  | 96 | 115 | 48 | 1.8
54 |  | M | Installation Complete |  | 53
55 |  | Training
56 |  |  | Develop Training Plan |  | 4 | PM | 20 |  |  |  |  | 20 | 20 | 1.2
57 |  |  | Organise Training Sessions |  | 56 | PM | 20 |  |  |  |  | 20 | 20 | 1.2
58 |  |  | Monitor Performance |  | 57 | PM | 20 |  |  |  |  | 20 | 20 | 1.2
59 |  | M | Training Complete
60 |  | Close Project
61 |  |  | Produce Project Completion Report |  | 54 | PM, BA, A | 7 | 6 | 6 |  |  | 9 | 6 | 0.2
62 |  |  | Gather Authorized Completion Report |  | 56 | PM, C | 9 |  |  |  |  | 9 | 9 | 0.1
63 |  | M |  | Completion Report Authorized | 57
64 |  |  | Evaluation
65 |  |  |  | Organize and Evaluation Seminar | 54 | PM, BA, A, D1, D2, C | 12 | 12 | 12 |  | 70 | 106 | 12 | 0.7
66 | [5 empty] | D3, D4, C
|  | M |  | Project Completed | 60
[6 empty] | TOTAL | 990 | 180 | 653 | 10 | 826
[6 empty] | Rate ($) | 125 | 90 | 110 | 100 | 60
[6 empty] | Cost ($) | $123, 750.00 | $16, 200.00 | 71830 | 1000 | 49560
[6 empty] | Labour | $262, 340.00
[6 empty] | Server | 6000
[6 empty] | Workstations | 4000
[6 empty] | Database | 7000
[6 empty] | User Interface Tool | 8000
[6 empty] | Training | 7500
[6 empty] | Total Budget | 294840